## Slide 1: UNDP GCF/GEF Project Document Template
UNDP requirements + GCF/GEF policies and guidelines

## Slide 2: Options Segregation of oversight / execution

## Slide 3
BPPS Nature Climate and Energy
Project Board
UNDP Project Assurance
UNDP Governance Arrangements for GCF and GEF Projects
Regional Bureau
Oversight
First line of defense
Oversight
Second line of defense
Implementing Partner
Project Management Unit
Execution
General RBX oversight functions:
UNDP compliance checks
Portfolio level oversight
Enhanced oversight
Cancel/suspend project
Escalate to UNDP Risk Committee
General UNDP project assurance
functions: GCF/GEF Fee services
UNDP compliance (e.g., risk management; project QA; evaluations;
GCF/GEF compliance (e.g., quality assurance of APR, Interim Evaluation, Terminal Evaluation, core indicators etc..)
Technical oversight
Quality assurance of project
General BPPS NCE oversight functions:
GCF/GEF Fee services
GCF/GEF compliance checks
Technical oversight
Revoke project DOA
Approve/reject project amendments
Enhanced oversight
Cancel/suspend project
Escalate to UNDP Risk Committee
General Project Board functions: UNDP role on project board GCF/GEF Fee service
Oversight of project execution (including COS)
Approval key project execution decisions
Quality assurance of project
Responsible Parties
UNDP project support to NIM
General execution functions:
Day-to-day execution and management of the project
Report on the project
Charged to project budget not GEF/GCF Fee
Note the Third Line of defense is comprised of independent OAI, IEO and other UNDP bodies.

## Slide 4: Segregation of oversight and execution in project governance arrangements
Project Governance Arrangements
Project Board/Steering Committee |  | 
Development Partner (supplier) | Project Executive | Beneficiary Representatives
UNDP Project Assurance
Implementing Partner
Project Support (e.g. Project Management Unit)
UNDP project support to NIM if requested by Implementing Partner
(if applicable)
Responsible Party B
(if applicable)
Responsible Party C
(others can be added as needed)
Oversight
& approval
of key execution decisions
Execution
Separation:
UNDP role on Project Board oversees project execution to ensure compliance with UNDP and GCF/GEF policies
Support to UNDP role on Project Board cannot be from same people who provide project assurance or execution
Separation:
UNDP role in execution performed by a department/unit that is not involved project assurance functions
Oversight of execution support cannot be done by same people who provide project assurance or who support the RR
Firewall

## Slide 5: Full NIM with Government as Implementing Partner
Project Governance Arrangements
Project Board/Steering Committee |  | 
Development Partner (supplier) UNDP Resident Representative (RR) | Project Executive Typically, senior representative of the national government entity; often it is supplemented by GCA rep. | Beneficiary Representatives Civil society, industry associations. other ministries, etc.
Project Assurance
UNDP Country Office Environment Focal Point (EFP)
Implementing Partner
National Government Entity
Project Support (e.g. Project Management Unit)
Responsible Party A
(if applicable)
Responsible Party B
(if applicable)
Responsible Party C
(if applicable)
Second line of defense
Regional Bureau oversees RR and Country Office compliance at portfolio level.
BPPS NCE RTA oversees technical quality assurance and GCF/GEF compliance. BBPS NCE PTA oversees RTA function.
UNDP NCE Executive Coordinator and Regional Bureau Deputy Director can revoke DOA/cancel/suspend project or provide enhanced oversight.

## Slide 6: Supported NIM with Government as Implementing Partner
Project Governance Arrangements
Project Board/Steering Committee |  | 
Development Partner (supplier) UNDP Resident Representative (RR) | Project Executive Typically, senior representative of the national government entity; often it is supplemented by GCA rep. | Beneficiary Representatives Civil society, industry associations. other ministries, etc.
Project Assurance
UNDP Country Office Programme Focal point (cannot be same team/person as those providing oversight or support to NIM or supporting RR on Project Board (could be, EFP, governance focal point)
Implementing Partner
National Government Entity
Project Support (e.g. Project Management Unit)
UNDP project support to Implementing Partner
Cannot be same team/person as project assurance or providing programmatic oversight support to RR (could be another programme person, operational staff, or IPSA or NPSA)
Responsible Party B
(if applicable)
Responsible Party C
(if applicable)
First line of defense
UNDP oversight of project support to IP cannot be UNDP staff providing project assurance or providing programmatic oversight support to the RR
Second line of defense
Regional Bureau oversees RR and Country Office compliance at portfolio level.
BPPS NCE RTA oversees technical quality assurance and GEF/GCF compliance. BBPS NCE PTA oversees RTA function.
UNDP NCE Executive Coordinator and Regional Bureau Deputy Director can revoke DOA/cancel/suspend project or provide enhanced oversight.

## Slide 7: UNDP Country Office as Implementing Partner (DIM)
Project Governance Arrangements
Project Board/Steering Committee |  | 
Development Partner (supplier) Typically, senior representative of the national government entity; often it is supplemented by GCA rep. | Project Executive UNDP Resident Representative (RR) | Beneficiary Representatives Civil society, industry associations. other ministries, etc. In DIM, this could also be the national government on whose behalf the project is implemented
Project Assurance
UNDP Country Office Deputy RR (or Environment Focal Point if not involved in execution or supporting RR on Project Board)
Implementing Partner
Dedicated UNDP Country Office department/unit executes project. IP Representative cannot be RR who is on Project Board or person providing project assurance (could be EFP or IPSA or NPSA)
Project Support (e.g. Project Management Unit)
Cannot be people from the same department/unit that provides project assurance or supporting RR on Project Board (could be IPSA or NPSA)
Responsible Party A
(if applicable)
Responsible Party B
(if applicable)
Responsible Party C
(if applicable)
First line of defense
UNDP role as Implementing Partner cannot be UNDP staff providing project assurance or providing programmatic oversight support to the RR
Second line of defense
Regional Bureau oversees RR and Country Office compliance at portfolio level.
BPPS NCE RTA oversees technical quality assurance and GEF/GCF compliance. BBPS NCE PTA oversees RTA function.
UNDP NCE Executive Coordinator and Regional Bureau Deputy Director can revoke DOA/cancel/suspend project or provide enhanced oversight.

## Slide 8: UNDP Regional Hub as Implementing Partner
Project Governance Arrangements
Project Board/Steering Committee |  | 
Development Partner (supplier) | Project Executive UNDP Regional Hub Director | Beneficiary Representatives Civil society, industry associations. other ministries, etc.
Project Assurance
UNDP Regional Hub M&E or programme focal point
(cannot be involved in execution or supporting Hub Director on Project Board)
Implementing Partner
UNDP Regional Hub executes project.
IP Representative cannot be Hub Director on Project Board or those providing project assurance (could be IPSA or NPSA)
Project Support (e.g. Project Management Unit)
Cannot be same people providing project assurance or supporting Project Board (could be IPSA or NPSA)
Responsible Party A
(if applicable)
Responsible Party B
(if applicable)
Responsible Party C
(if applicable)
First line of defense
UNDP role as Implementing Partner cannot be UNDP staff providing project assurance or providing programmatic oversight support to the RHD
Second line of defense
Regional Bureau oversees Regional Hub Director and Regional Hub staff compliance at portfolio level
BPPS NCE RTA oversees technical quality assurance and GCF/GEF compliance. BBPS NCE PTA oversees RTA function.
UNDP NCE Executive Coordinator and Regional Bureau Deputy Director can revoke DOA/cancel/suspend project or provide enhanced oversight.

## Slide 9: UNDP BPPS NCE as Implementing Partner
Project Governance Arrangements
Project Board/Steering Committee |  | 
Development Partner (supplier) | Project Executive Cannot be same UNDP person providing project assurance or involved in execution (could be Deputy Bureau Director or PTA) | Beneficiary Representatives Civil society, industry associations. other ministries, etc.
Project Assurance
Cannot be same UNDP person supporting Project Board or involved in execution (could be BPPS NCE PTA or RTA)
Implementing Partner
BPPS NCE executes the project. IP representative cannot be same person on Project Board or providing project assurance (could be IPSA)
Project Support (e.g. Project Management Unit)
Cannot be same people providing project assurance or supporting Project Board (could be IPSA)
Responsible Party A
(if applicable)
Responsible Party B
(if applicable)
Responsible Party C
(if applicable)
First line of defense
UNDP role as Implementing Partner cannot be UNDP staff providing project assurance or providing programmatic oversight support to BPPS role on Project Board
If PTA on Project Board, RTA providing project assurance must be from different technical team not reporting to PTA on Project Board
Second line of defense
UNDP NCE Executive Coordinator and BPPS Director can revoke DOA/cancel/suspend project or provide enhanced oversight

## Slide 10: UN Agency or CSO as Implementing Partner for Regional/Global Projects overseen by BPPS NCE
Project Governance Arrangements
Project Board/Steering Committee |  | 
Development Partner (supplier) UNDP BPPS NCE (could be BPPS NCE PTA) | Project Executive UN Agency or CSO | Beneficiary Representatives Civil society, industry associations. other ministries, etc.
Project Assurance
Cannot be same UNDP person supporting Project Board (could be BPPS NCE RTA)
Implementing Partner
UN Agency or CSO executes the project
Project Support (e.g. Project Management Unit)
Responsible Party A
(if applicable)
Responsible Party B
(if applicable)
Responsible Party C
(if applicable)
First line of defense
If PTA on Project Board, RTA providing project assurance must be from different technical team not reporting to PTA on Project Board
UNDP function on Project Board must be BPPS NCE not Regional Hub.
Second line of defense
UNDP NCE Executive Coordinator and BPPS Director can revoke DOA/cancel/suspend project or provide enhanced oversight