DELEGATION OF AUTHORITY

Adaptation Fund Contribution to:

Name of Country:

Full Project Title:

PIMS ID:

Project Type:

Quantum  BU:

Quantum Project ID

Quantum Award ID:

BPPS/Thematic Hub:

(the “Project”)

The project, which amounts to a total of US$ [amount of AF project budget excluding the AF Implementing Entity Fee], has received its final approval [add link (in hyperlink format, do not place the link address) to relevant AF letter in PIMS+] in accordance with the established policies and guidelines of the Adaptation Fund (AFB notice of approval attached, Annex 1) and grant agreement (attached, Annex 2). With this approval, I am pleased to send for your signature this Delegation of Authority.

By accepting this Delegation of Authority, the Resident Representative [or Regional Hub Manager] assumes full responsibility and accountability to sign the Project Document for this Project and to ensure the timely implementation of this AF-financed project. The Resident Representative [or Regional Hub Manager] shall ensure that the project complies with the AF-specific requirements outlined below and in the Project Document and shall provide oversight and quality assurance of tasks undertaken by the Implementing Partner and/or Responsible Parties. In addition, as with all UNDP projects, the Resident Representative [or Regional Hub Manager] assumes full accountability for ensuring that all requirements set out in UNDP’s Programme and Operations Policies and Procedures (POPP), its Financial Regulations and Rules and Internal Control Framework are complied with.

By accepting this Delegation of Authority, the Regional Bureau Director assumes full responsibility and accountability to provide oversight to the Resident Representative [or Regional Hub Manager] to ensure compliance with all UNDP regulations and rules. In addition, the Regional Bureau Director will ensure that the Deputy Regional Bureau Director provides additional support to the BPPS Planet Hub and Quality and Impact Hub when needed to ensure the AF-specific requirements noted below and in the Project Document are met as required and as per the noted schedule.

Should this project be at-risk of non-compliance with any AF requirement and deadlines, including the AF Minimum Fiduciary Standards, the risk shall be escalated by the Resident Representative [or Regional Hub Manager] to the Deputy Regional Bureau Director for action. The BPPS Quality and Impact Hub and BPPS Planet Hub should be informed of risks of non-compliance. If such risks of non-compliance are not adequately addressed, the BPPS Vertical Funds Executive Coordinator shall retain the authority to suspend or revoke the Delegation of Authority, and if necessary, after consultation with the Regional Bureau Director, transfer the accountability and responsibility for the implementation of this project to another unit (e.g. the Regional Bureau) or, with the agreement of the AF, suspend or cancel this project.

AF specific conditions and deadlines:

| - AF Conditions: if these conditions are not met this project may be suspended or cancelled by the BPPS Vertical Funds Executive Coordinator. |  |  |  |
| --- | --- | --- | --- |
| 1 | AF Fee | The total AF Fee over the lifetime of this AF project shall be [USD XX - amount to be inserted as the fee approved by the donor]. The AF Fee shall only be used for the intended purpose and applied in relation to the performance of oversight services as per AF Policies and Procedures. The AF Fee may be returned to the AF in the event of non-compliance with the POPP and/or AF project management requirements. Please note that the fee share to the country Office (CO) [or Regional Hub] is allocated based on annual delivery projections and should be included in the annual IB allocation the CO receives from the Regional Bureau. [or …allocation the Regional Hub receives.] |  |
| 2 | Functional separation between oversight and execution support | No CO execution support services shall be provided to the Project unless approved by the AF. Execution services will only be approved by the AF on an exceptional basis upon receipt of both a written request from UNDP with a strong rationale for the provision of direct services and a letter by the recipient country’s Designated Authority. Any execution support services so agreed shall be performed in full compliance with UNDP guidance and AF policies and procedures, which shall require the Country Office to ensure and maintain a functional separation and reporting lines between staff and non-staff personnel providing oversight services and those providing execution support services. |  |
|  |  | Where execution support services have been approved by the AF, the LOA with the Government to provide CO support has been duly completed, cleared by BPPS Quality and Impact Hub, signed by the relevant parties and included as an annex to the Project Document before signature by the Implementing Partner, Government Coordinating Agency and UNDP. |  |
|  |  | Service costs in relation to execution support shall be charged in accordance with the project budget approved by the AF. |  |
|  |  | UNDP staff and non-staff personnel engaged in execution support services shall under no circumstances be involved in oversight services (and vice versa). |  |
|  |  | The staffing arrangements on oversight ensures a strict functional separation between oversight and execution. |  |
| 3 | Co-financing | The Resident Representative [or Regional Hub Manager] shall ensure that cost-sharing arrangements are documented in line with POPP guidance, shall ensure monitoring of the status and amount of committed and applied/realized co-financing included in the Project Document, and shall report on the amount realized with supporting evidence in the PPR only during the years that an MTR or FE are undertaken. The Country Office shall also provide information on the realized amount of co-financing to the independent consultants carrying out the Mid-Term Review (if required) and Final Evaluation for their review and verification. The Country Office shall inform the BPPS Quality and Impact and BPPS/Planet Hub immediately in the event of any material changes in realized co-financing. |  |
| 4 | Project revisions | All revisions/amendments to what was included in the Project Document shall follow the procedures set out in the RACI/POPP, which shall include approval by the BPPS RTA and PTA assigned to this project for oversight. The Country Office [or Regional Hub] shall ensure that the BPPS RTA shall be duly informed within the timelines set out in POPP and the BPPS RTA and PTA shall consult with the BPPS Quality and Impact Hub and liaise with the AF, as required. If the proposed changes are deemed by the BPPS RTA and PTA to be major amendments, additional BPPS Quality and Impact Hub and AF approvals are necessary. |  |
| 5 | Annual oversight missions | The Country Office person responsible for oversight of this project shall supervise the implementation of this project and undertake annual site missions, charged to the AF fee. |  |
| 6 | Budget Revisions | Project budget deviations are not permitted other than in accordance with the AF Legal Agreement. Budget revision proposals must be cleared by VF Financial Oversight Team and approved by BPPS RTA assigned to this project for oversight in PIMS+ before it is approved in Quantum. The project budget cannot be increased above the amount already approved by the AF. Therefore, any over-expenditure on this project must be absorbed by other Country Office [or Regional Hub] resources. |  |
|  |  | A minimum of one budget revision annually: The Country Office must submit a budget revision (multi-year) to the BPPS RTA through PIMS+, requesting clearance. All budget revisions must be approved by the BPPS RTA and cleared by the VF Financial Oversight Team. |  |
| 7 | AF branding | The AF logo shall be displayed along with the UNDP logo where appropriate and relevant, and UNDP should endeavor to maximize opportunities for acknowledging the identity of the Adaptation Fund, line with the AF legal Agreement and UNDP’s branding guidelines. |  |
| 8 | Project extensions | Project extensions are unfunded by the AF and UNDP and, in general, are not permitted. Extensions must follow the BPPS Quality and Impact Hub project extension guidance. Under exceptional circumstances and subject to the conditions set out in the BPPS Quality and Impact Hub project extension guidance for the submission of a request for extension to the vertical funds, the Resident Representative [or Regional Hub Manager] shall coordinate with the BPPS RTA and PTA assigned to this project for oversight, within the deadlines set out in the VF project extension guidance, for the internal clearance and submission of the request for approval by the BPPS VF Executive Coordinator (in coordination with the AF, where required). The BPPS VF Executive Coordinator shall consult the Regional Bureaux (RBX) and may reject the extension request if no external (non-AF) financing by the IP or internal UNDP CO resources for the additional oversight cost of UNDP can be identified. |  |
|  |  | Should an extension be approved by the BPPS VF Executive Coordinator (in coordination with the AF, where required), the additional oversight costs for the Country Office/Regional Hub and BPPS/Quality and Impact Hub shall be covered by other resources and cannot be charged to the project budget. At the time of extension requests, the source of funds to cover such additional costs to UNDP should be declared by all relevant units as part of the extension request. |  |
| 9 | Project Document Signature and project start | The Resident Representative [or Regional Hub Manager] shall sign and obtain the requisite signature(s) of the representative of the Implementing Partner (as well as signature by the representative of the Government if necessary) and shall achieve this milestone by a benchmark date of no later than 5 months from the final Fully Developed Project AF Board Approval date. For multi-country projects, the Resident Representative [or Regional Hub Manager] shall request and obtain receipt of the signed signature pages from participating countries. For projects implemented by an NGO/IGO, the Resident Representative [or Regional Hub Manager ] shall also obtain receipt of the signed Project Cooperation Agreement. The Resident Representative [or Regional Hub Manager] shall notify the Regional Program Associate of the BPPS Planet Hub in order to upload a copy of the signed project document to PIMS+. In the event that a signature is not secured by the deadline, the BPPS Quality and Impact Hub and BPPS PTA and RTA, with the support of the CO/Regional Hub, will discuss with the AF Secretariat and the Designated Authority for AF matters at the country level on whether the project should be restructured and/or cancelled. | [PA: Add deadline that is 5 months after AF Board Approval of the Fully Developed Proposal.] |
| 10 | Inception Workshop & Inception Report | The inception workshop marks the official start date of the project under AF Policies. The Resident Representative shall ensure that the inception workshop shall be held no later than 4 months after the first disbursement is received from the AF Trustee. Any delays will require extension approvals from the AF, which may not be granted without appropriate justification. It is noted however that, given the strict reporting deadlines at project closure stage, the inception workshop must be held during Q1 or Q2, such that project completion will also be achieved during Q1 or Q2. The Country Office must ensure that the inception report is completed, shared with the BPPS RTA and PTA for technical review and clearance and review by the BPPS Quality and Impact Hub RBM focal point and finalized within 2 weeks of the inception workshop date. The Country Office must share the cleared inception report for approval by the Project Board no later than 1 months after the Workshop date, as per the AF Legal Agreement. The BPPS RTA and PTA shall notify AF Secretariat and submit a copy of the report as per AF Policy requirements. | Estimated Inception Workshop Deadline: [PA: Enter date that is no more than 4 months from the first AF disbursement and no later than May 31] [For October approved projects, the Inception Workshop should not take place later than May of the last year of implementation. For April approved projects, the Inception Workshop should not take place later than January of the last year of implementation.] |
| 11 | Project Performance Report (PPR) | The Country Office shall, together with the project team, complete a high quality draft AF PPR with evidence to support progress by the designated due date. The Deputy Resident Representative shall clear the PPR and submit for review by the BPPS RTA and VF Financial Oversight Team. The Resident Representative [or Regional Hub Manager] shall ensure all comments are addressed and share the final PPR for submission by the BPPS Planet Hub prior to the deadline. | Annually The 1st PPR must be submitted one year from the date of the inception workshop. Subsequent PPRs shall be submitted no later than two months after the end of the reporting year. The last PPR will be submitted six months after project completion. This will be considered the project completion report (PCR). |
| 12 | Mid-Term Review | The Resident Representative shall ensure that a mid-term review will be undertaken by an independent third-party evaluator, as per UNDP and AF requirements, and the draft shared with relevant stakeholders for review and comments before the indicated submission deadline. The CO M&E focal point and Resident Representative [or Regional Hub Manager] shall clear and submit the final mid-term review report to the BPPS RTA. The BPPS RTA shall review and clear the final mid-term review report together with the CO. The Resident Representative shall ensure that the mid-term review report is finalized and cleared before the due date to ensure on-time submission by the BPPS Quality and Impact Hub to the AF. The Resident Representative [or Regional Hub Manager] shall ensure that the mid-term review report management response is completed with the BPPS RTA’s input as per the required timeline. Mid-Term Review costs is not covered by AF project budget, it will have to be covered by other CO resources, as per AF rules https://www.adaptation-fund.org/generic/costs-and-fees/ . | Estimated Mid-Term Review deadline: [PA: Add deadline as per ProDoc]. |
| 13 | Project completion | The Resident Representative [or Regional Hub Manager] shall ensure that this project shall reach project completion by the completion date. This date is the expected completion date, calculated as the date of Inception Workshop plus project duration, which is the date upon which execution of all activities for the Project must be completed. No activities, except for the final clearance of the Terminal Evaluation Report and the corresponding management response and the end-of-project review Project Board Meeting should take place after the Completion Date. The Project completion report must be finalized and shared with the Adaptation Fund no later than 4 months after Project Completion date. | Estimated Project Completion Date: [PA: add date calculated based on estimated Inception Workshop date plus project duration and that is no later than 30 September of that year in order to meet the requirement to report the Project Closure in due time.] |
| 14 | Final Evaluation (FE) | The Resident Representative [or Regional Hub Manager] shall ensure that a final evaluation will be undertaken by an independent third-party evaluator, as per UNDP and AF requirements, and the draft shared with relevant stakeholders for review and comments. The final evaluation must be submitted to the AF Secretariat and Designated Authority within 4 months of project completion. The CO M&E focal point and Resident Representative [or Regional Hub Manager] shall clear and submit the final terminal evaluation report to the BPPS RTA. The BPPS RTA and PTA shall review and clear the final terminal evaluation report together with the CO. The Resident Representative [or Regional Hub Manager] shall ensure that the final evaluation report is finalized and cleared before the due date to ensure on-time submission by the BPPS Quality and Impact Hub to the AF. The Resident Representative [or Regional Hub Manager] shall ensure that the final evaluation report management response is completed with the BPPS RTA’s input as per the required timeline. The BPPS VF Executive Coordinator shall be entitled to withhold payment of the AF Fee in the event of delay of the terminal evaluation. Final Evaluation costs will have to be covered by other CO resources https://www.adaptation-fund.org/generic/costs-and-fees/ and not by the project budget. | Estimated Final Evaluation Deadline: [PA: Add deadline (as per ProDoc)] Final Evaluation must be finalized and shared with the AF within 4 months from Project Completion. |
| 15 | Project operational closure | The Resident Representative [or Regional Hub Manager] shall ensure that this project is operationally closed by the indicated deadline. Operational Closure must take place within 5 months of Project Completion. | Estimated Project Operational Closure deadline: [PA: Add deadline that is 5 months from Project Completion] Project operationl closure must take place within 5 months of Project Completion. |
| 16 | Project financial closure | The Resident Representative [or Regional Hub Manager] shall ensure that this project shall be financially closed (and supporting documents to the financial closure should be submitted to BPPS Quality and Impact Hub) within 6 months after Operational Closure, and no later than 11 months after Project Completion date. Failure to financially close the project by the above deadline will result in the elevation of the CO to a high-risk category and no further vertical fund programming will be undertaken until overdue closures are addressed. | Estimated Project Financial Closure Deadline: [PA: Add deadline that is 6 months after operational closure and must never be more than 11 months] |

By signing this Delegation of Authority, the signatories also agree to:

- Immediately inform each other of any circumstances that may indicate potential misuse of project funds, non-compliance with the SES policies, a breach (or potential breach) of UNDP’s policy framework or the legal terms and conditions set out in the UNDP Project Document and/or AF requirements

- Actively discuss project issues that may jeopardize the timely implementation of the Project or the achievement of the agreed results and/or outcomes as stated in the Project Document.

- Assess future programming requests for vertical fund programming by the country considering existing performance and capacity constraints at all levels.

This Delegation of Authority shall enter into force upon the date of execution (as written below) by all signatories, and shall remain in force until all legal liabilities towards AF in relation to the Project have ceased, unless revoked earlier by the BPPS VF Executive Coordinator.

A copy of this Delegation of Authority shall be provided to:

[Name of Regional Bureau Deputy Director - Deputy Director, Bureau acronym]

[Name of Regional Hub Manager, Manager, Name and location of Hub]

[Name of DRR (Programmes), Title, UNDP Name of City, Country]

[Name of Country Director, Country Director, UNDP Name of City, Country]

[Name of Country Advisor - Country Advisor, Location of Country Advisor]

[Name of Country Support person (Desk Officer), Country Support Team, Location]

[Name of Environment Focal Point at the CO, Title, UNDP Name of City, Country]

[Name of Regional Team Leader, Location]

[Name of Regional Technical Advisor (RTA), UNDP Thematic Hub]

[Name of Principal Technical Advisor (PTA), UNDP Thematic Hub]

This Delegation of Authority is signed for agreement and acceptance by and between:

| Nancy Bennet Director, Quality and Impact Hub Executive Coordinator, Vertical Funds Bureau for Policy and Programme Support UNDP | Date: Signature: |
| --- | --- |
| Marcos Neto Assistant Administrator and Director Bureau for Policy and Programme Support UNDP | Date: Signature: |
| Accepted By: [Regional Bureau Director, [Bureau acronym] | Date: Signature: |
| Accepted By: [Resident Representative] | Date: Signature: |

Annexes

Annex 1		AFB notice of approval

Annex 2		Copy of the Legal Agreement with the AFB

[Please ensure the Legal Agreement is attached to the DOA.]

Please find the Grant Agreement attached.