## Sheet1
Office Closure Plan for [Name of Presence]
Item | Action * | Responsible | Due date
Confirmation of closure | Launch the review of the presence according to provisions in business case
Consultations with counterparts | Discuss the decision to close and implications with local authorities and government representatives
Programme coverage after closure | Review all on-going project activities within the Country Programme, together with those undertaken by Agencies within their regular programmes, and make recommendations regarding their continued coverage subsequent to the closure.
Decommissioning of Sub office Premises | Prepare hand over of premises to the local community to establish a community centre.
Separation or Transfer of Personnel | Send notice to FTA staff for relocation / change of duty station; send contract termination notice to TA staff.
Clearing of any Pending/Open Financial Transactions; | Establish a list of pending payments;
Accounting Records and their Disposal | Send memo to communicate arrangements for the future processing of pending transactions to all staff;
Reconcile and close petty cash account.
Prepare all accounting records for transfer to Country Office.
Closing of Bank Accounts and Deactivation of ATLAS BU/Department | Consult UNDP treasury and close local bank account (allowing some time to enable issued checks to be presented to the bank before closure).
Clarify arrangements for possible submission of late invoices.
Disposal of Equipment | Prepare proposal for transfer of project assets
Convene project steering committee
Launch asset transfer
Disposal of Files | Prepare all files for transfer to Country Office.
Transfer files.
Notice to Partners of Closure and Revised Channels of Interaction | Issue a circular to inform organizations of the UN System as well as all other relevant partners, including the host Government, of the impending closure of the sub office.
Close-out activity plan and status review with HQ RBX | Seek clearance of close-out plan from RBX HQ including progress update
Final sign off from BOM for related activities | Seek final sign off from BOM for the implementation of all agreed close-out activities related to BOM
* Please delete / add / amend activities as approriate