## RACI Definitions
RACI for GEF oversight
Responsible | This is the person or small group of people responsible to get the job done. If several people are responsible, a lead person has been identified (shaded in grey) who is ultimately responsible for the work of the entire group.
Accountable | This person approves the work done by those responsible and takes the final decision linked to that task. The accountable person is held to account by UNDP if something goes wrong.
Consulted | These people must be consulted before certain work is performed and approved. They are typically subject matter experts.
Informed | These are people with no active participation in the task and don’t have to be consulted, but must be made aware of updates or decisions. Their input or feedback is generally not needed to keep a task going, but the outcome can have a direct or indirect impact on them.
N/A | none of the above. Does not need to be informed.

## RACI GEF portfolio level
Corporate Tasks required by GEF | Sub-Task | Country Office Oversight | Regional Bureau Oversight | BPPS NCE/VF Oversight | [7 empty] | HQ Units
|  |  |  | VF Executive Coordinator/ VF Directorate | RTL | PTA | RTA | Finance HQ | RBM/ safeguards | Global PA | Directorate | OFRM | BMS | IEO | OAI | BERA
GEF Policy Support | Development, revision and operationalization of GEF policies, strategies, business plans and guidelines | Informed | Informed | Accountable | [6 empty] | Responsible | Consulted | Consulted | Consulted | Consulted | n/a
| Participation in the meetings of the GEF governing bodies. | Informed | Informed | Accountable | [6 empty] | Responsible | n/a | n/a | n/a | n/a | n/a
Portfolio management | Pipeline and program management (includes risk management, consultations with GEF Council members etc..) | n/a | Consulted | Accountable | [6 empty] | Responsible | n/a | n/a | n/a | Consulted | n/a
| Financial management and data management, participation in financial consultations organized by the Trustee. | n/a | n/a | Accountable | [6 empty] | Responsible | Consulted | n/a | n/a | n/a | n/a
| Annual Monitoring Report (AMR) | Informed | n/a | Accountable | [6 empty] | Responsible | n/a | n/a | n/a | n/a | n/a
| Annual Portfolio Review for the Evaluation Office (APR) | Informed | n/a | Accountable | [6 empty] | Responsible | n/a | n/a | Consulted | n/a | n/a
| Reporting includes all the reporting requirements as per the Guidelines | Informed | n/a | Accountable | [6 empty] | Responsible | n/a | n/a | n/a | n/a | n/a
Outreach and knowledge | Participation in sub-regional consultations, Country Support Program (CSP) activities and STAP meetings | Informed | Informed | Accountable | [6 empty] | Responsible | n/a | n/a | n/a | n/a | n/a
| Media queries | n/a | n/a | Accountable | [6 empty] | Responsible | n/a | n/a | n/a | n/a | Consulted
Support to Independent Evaluation Office | Includes evaluations, reviews and studies initiated by the GEF Independent Evaluation Office. | Informed | Informed | Accountable | [6 empty] | Responsible | n/a | n/a | n/a | n/a | Informed

## Final RACI project level
Oversight (covered by GEF Fee) | Sub-Task (covered by GEF Fee) | Country Office Oversight | [5 empty] | Regional Bureau Oversight |  |  |  |  | BPPS NCE/VF Oversight | [9 empty] | Government Oversight NOT EXECUTION |  | GEF
|  | Resident Representative | Deputy Resident Representative | Programme Officer | M&E | Operations | # days | Director | Deputy Director | Desk Officer |  | # days | VF Executive Coordinator | Regional Team Leader | Principal Technical Advisor | Regional Technical Advisor | Regional PA | Finance HQ | Regional MPSA | RBM/ safeguards | Global PA | # days | GEF OFP | Implementing Partner/ PMU | Secretariat | Council
Project Origination | Pre-Investment Proposal Preparation | Accountable | Responsible | n/a | Consulted | Consulted |  | n/a | Consulted | Consulted |  |  | n/a | Consulted | Consulted | Consulted | Informed | n/a | Consulted | n/a | n/a |  | Consulted | Consulted | n/a | n/a
| Pre-Investment Screening Committee (PSIC) Review | Consulted | n/a | n/a | Consulted | Consulted |  | n/a | Informed | Consulted |  |  | n/a | Accountable | Responsible | Consulted | Responsible | n/a | Consulted | Consulted | n/a |  | n/a | n/a | Consulted | n/a
| Approve or reject PSIC decision | Informed | n/a | n/a | Informed | Informed |  | Informed | n/a | n/a |  |  | Accountable | Responsible | Responsible | n/a | Informed | n/a | Informed | n/a | Informed |  | Informed | Informed | n/a | n/a
PIF development | Draft PIF, pre-SESP and other required documents. Secure GEF Country-level Operational Focal Point letter. | Consulted | Accountable | Responsible | Consulted | Consulted |  | n/a | n/a | Informed |  |  | n/a | n/a | Consulted | Consulted | Consulted | n/a | Consulted | n/a | n/a |  | Consulted | Consulted | n/a | n/a
| Clearance of draft PIF and other required documents for compliance with UNDP POPP and submit to BPPS NCE/VF for GEF quality assurance | Accountable | Responsible | Responsible | Consulted | Consulted |  | n/a | n/a | Consulted |  |  | n/a | Informed | informed | Consulted | Informed | n/a | Informed | n/a | n/a |  | n/a | n/a | n/a | n/a
| GEF Safeguards quality assurance | n/a | n/a | Informed | Consulted | Consulted |  | n/a | n/a | Informed |  |  | n/a | n/a | Consulted | Accountable | Consulted | n/a | n/a | Responsible | Informed |  | n/a | n/a | n/a | n/a
| GEF Technical quality assurance (Incl. the GEF Gender policy) and submission to GEF | n/a | n/a | Informed | n/a | n/a | n/a | n/a | n/a | n/a |  |  | n/a | n/a | Accountable | Responsible | Consulted | n/a | n/a | n/a | Informed |  | n/a | n/a | n/a | n/a
| Respond to GEF Secretariat/STAP review | n/a | Consulted | Responsible | Consulted | Consulted |  | n/a | n/a | n/a |  |  | n/a | Informed | Responsible | Accountable | Consulted | Consulted | Consulted | Consulted | Informed |  | Consulted | Consulted | Responsible | n/a
| PIF approval by GEF Council (release by GEF Trustee of 20% GEF Fee to UNDP) | Informed | Informed | Informed | Informed | Informed |  | n/a | Informed | Informed |  |  | Informed | Informed | Accountable | Responsible | Informed | Informed | Informed | n/a | Informed |  | Consulted | Informed | Approves | n/a
PPG preparation | Prepare GEF Project Preparation Grant/Initiation Plan
| Delegate authority for GEF PPG resources to Country Office (GEF financial and technical clearances, DOA signed by RR, RBX and EC) | Responsible | Informed | Informed | Informed | Informed |  | Responsible | Informed | Informed |  |  | Accountable | n/a | Responsible | Consulted | Responsible | Responsible | Informed | n/a | Responsible |  | n/a | n/a | n/a | n/a
| Draft, sign, implement PPG/Initiation Plan (Undertake due diligence, confirm implementation modality, supervise country consultations etc..). | Accountable | Responsible | Consulted | Consulted | Consulted |  | n/a | Informed | Informed |  |  | n/a | Informed | Consulted | Consulted | Consulted | n/a | n/a | n/a | n/a |  | Informed | Consulted | n/a | n/a
| Complete OAI Audit checklist required by GEF Secretariat and Council (to be signed by RR and EC) | Accountable | Responsible | Consulted | Consulted | Consulted |  | Informed | Responsible | Consulted |  |  | Responsible | Consulted | n/a | Consulted | Consulted | n/a | Consulted | Infomred | n/a |  | Informed | Consulted | Clear | Approve
| If Government requests implementation support, negotiate with GEF Secretariat for exceptional request | Consulted | Consulted | Informed | Consulted | Consulted |  | n/a | Consulted | Informed |  |  | n/a | Consulted | Accountable | Responsible | Informed | n/a | Informed | n/a | n/a |  | Consulted | Consulted | Approves | n/a
| Financial managment and implementation of PPG/IP project in ATLAS in accordance with UNDP POPP requirements | Accountable | Responsible | Consulted | Consulted | Consulted | n/a |  | n/a | Consulted |  | n/a | n/a | Consulted | n/a | Consulted | Informed | Informed | Informed | n/a | n/a | n/a | Consulted | Consulted | n/a | n/a
Clearance of project document and other required documentation for submission to GEF for CEO endorsement before GEF cancellation deadline
Clearnce of draft pro | Clearance of draft UNDP GEF project document and annexes for compliance with UNDP POPP (including private sector due diligence, QA, SES etc…) and submission within deadlines to BPPS NCE/VF | Accountable | Responsible | Consulted | Consulted | Consulted |  | n/a | n/a | Informed |  |  | n/a | n/a | n/a | Consulted | Informed | n/a | Informed | Informed | n/a |  | Informed | Consulted | n/a | n/a
| GEF Safeguards quality assurance | n/a | Informed | Informed | Consulted | Consulted |  | n/a | n/a | Informed |  |  | n/a | n/a | Consulted | Accountable | Consulted | n/a | n/a | Responsible | Informed |  | n/a | Consulted | n/a | n/a
| GEF Financial quality assurance | n/a | Informed | Informed | Consulted | Consulted |  | n/a | n/a | Informed |  |  | n/a | n/a | Consulted | Responsible | Consulted | Accountable | Responsible | n/a | Informed |  | n/a | n/a | n/a | n/a
| GEF Technical quality assurance and submission to GEF within GEF cancellation deadlines or project automatically cancelled by GEF | n/a | Informed | Informed | n/a | n/a | n/a | n/a | n/a | Informed |  |  | n/a | n/a | Accountable | Responsible | Consulted | n/a | n/a | n/a | Informed |  | n/a | n/a | n/a | n/a
| Respond to GEF Secretariat/Council review | Informed | Informed | Responsible | Consulted | Consulted |  | n/a | n/a | n/a |  |  | n/a | n/a | Accountable | Responsible | Consulted | n/a | Consulted | n/a | Informed |  | Consulted | Consulted | Responsible | n/a
| LPAC | Accountable | Responsible | n/a | Consulted | Consulted |  | n/a | n/a | Informed |  |  | n/a | n/a | n/a | Consulted | Informed | n/a | Consulted | n/a | n/a |  | Informed | Consulted | n/a | n/a
| CEO endorsement by GEF CEO | Informed | Informed | Informed | Informed | Informed |  | Informed | n/a | Informed |  |  | Informed | Informed | Accountable | Responsible | Informed | Informed | Informed | n/a | Informed |  | Consulted | Informed | Approves | Approves when requests
Project Implementation | Delegate authority for GEF project resources to Country Office (GEF financial and technical clearances, DOA signed by RR, RBX and EC) | Responsible | Informed | n/a | Informed | Informed |  | Responsible | Consulted | Informed |  |  | Accountable | n/a | Responsible | n/a | Responsible | Responsible | Informed | n/a
| Project document signature by RR and IP | Accountable | Responsible | Informed | Informed | Informed |  | n/a | n/a | Informed |  |  | n/a | n/a | n/a | Informed | Informed | Informed | Informed | Informed | n/a |  | Informed | Accountable | n/a | n/a
| First disbursement of GEF funds (release by GEF Trustee of 50% of GEF Fee to UNDP) | Accountable | Responsible | n/a | Consulted | Consulted |  | n/a | n/a | Informed |  |  | n/a | n/a | n/a | Informed | Consulted | Informed | Informed | n/a | n/a |  | n/a | Consulted | n/a | n/a
| Inception Workshop | Consulted | Accountable | Responsible | Consulted | Consulted |  | n/a | n/a | Informed |  |  | n/a | Informed | n/a | Consulted | Consulted | n/a | n/a | n/a | n/a |  | Consulted | Consulted
| When approved by the GEF on an exceptional basis, execution support country support to the IP NOT COVERED BY GEF FEE TO BE SEPARATED FROM OVERSIGHT | Accountable | Cannot be involved in order to avoid a conflict of interest with oversight paid by GEF Fee | Cannot be involved in order to avoid a conflict of interest with oversight paid by GEF Fee | Cannot be involved in order to avoid a conflict of interest with oversight paid by GEF Fee | Same people involved in oversight cannot be involved in execution |  | n/a | Informed | Consulted | Informed |  | Cannot be involved in order to avoid a conflict of interest with oversight paid by GEF Fee | Cannot be involved in order to avoid a conflict of interest with oversight paid by GEF Fee | Cannot be involved in order to avoid a conflict of interest with oversight paid by GEF Fee | Cannot be involved in order to avoid a conflict of interest with oversight paid by GEF Fee | Cannot be involved in order to avoid a conflict of interest with oversight paid by GEF Fee | Cannot be involved in order to avoid a conflict of interest with oversight paid by GEF Fee | Cannot be involved in order to avoid a conflict of interest with oversight paid by GEF Fee | Cannot be involved in order to avoid a conflict of interest with oversight paid by GEF Fee | Cannot be involved in order to avoid a conflict of interest with oversight paid by GEF Fee | not oversight covered by GEF Fee/must be firewalled from oversight to avoid conflict of interest | Consulted | Accountable | Approve | Informed
| AWP: Review at CO level | Consulted | Accountable | Responsible | Informed | Consulted |  | n/a | n/a | n/a |  |  | n/a | n/a | n/a | Informed | Consulted | n/a | Informed | n/a | n/a |  | n/a | n/a | n/a | n/a
| AWP: GEF quality assurance | n/a | Informed | Informed | Informed | Consulted |  | n/a | n/a | Informed |  |  | n/a | Consulted | Consulted | Accountable | Consulted | Responsible | Responsible | n/a | n/a |  | n/a | n/a | n/a | n/a
| AWP: Clearance/approval | Accountable | Responsible | Informed | Consulted | Consulted |  | n/a | n/a | Informed |  |  | n/a | n/a | n/a | Informed | n/a | n/a | n/a | n/a | n/a | n/a | Informed | Responsible | n/a | n/a
| Regular oversight missions to validate, supervise, quality assure project management unit (Implementing Partner) and field work | Informed | Accountable | Responsible | Consulted | Consulted |  | n/a | n/a | Consulted |  |  | n/a | n/a | n/a | Consulted | Informed | n/a | n/a | Informed | n/a |  | Consulted | Responsible | n/a | n/a
| Supervision missions by the RTA - Troubleshooting missions to manage technical quality assurance risks | Informed | Consulted | Informed | Consulted | Consulted |  | n/a | Consulted | Informed |  |  | n/a | Responsible | Accountable | Responsible | Consulted | n/a | Informed | n/a | n/a |  | Consulted | Consulted | n/a | n/a
| GEF PIR: draft in consulation with IP and GEF OFP | Responsible | Accountable | Responsible | Consulted | Consulted |  | n/a | n/a | Informed |  |  | n/a | n/a | n/a | Responsible | Consulted | n/a | Consulted | n/a | Informed |  | Consulted | Responsible | n/a | n/a
| GEF PIR: quality assurance (in particular risk management and escalate risks as needed), finalize with CO and submit to GEF | Informed | Informed | Informed | Informed | Consulted |  | n/a | Consulted | Informed |  |  | n/a | n/a | Accountable | Responsible | Consulted | n/a | Responsible | Responsible
| Risk management: Manage project risks as per UNDP ERM | Accountable | Responsible | Consulted | Consulted | Informed |  | n/a | n/a | Informed |  |  | n/a | Informed | Informed | Consulted | Informed | Informed | Consulted | Consulted
| Risk management: GEF Project Escalated Risks/Critical issues (typically through Action Plan with options for additonal oversight or suspension or cancellation (RR, RBX and EC sign)) | Responsible | Informed | Informed |  |  |  | Consulted | Responsible | Informed |  |  | Accountable | Informed | Responsible | Informed |  | n/a |  | Informed
| MTR and GEF core indicators: Manage contracting and in-country consultation process according to GEF deadlines and guidance; draft management response; upload relevant documentation to UNDP ERC | Accountable | Responsible | Consulted | Consulted | Consulted |  | n/a | n/a | Informed |  |  | n/a | Informed | n/a | Consulted | Consulted | n/a | Consulted | Consulted | n/a |  | Consulted | Consulted | n/a | n/a
| MTR and GEF core indicators: quality assurance, provide input to CO on MTR and management response, sign off on final MTR report, and submission to GEF (release by GEF Trustee of 30% of GEF Fee to UNDP) | n/a | Informed | Informed | Informed | Consulted |  | n/a | Consulted | Informed |  |  | n/a | Accountable | n/a | Consulted | Consulted | n/a | Responsible | Responsible | n/a |  | Consulted | Responsible | n/a | n/a
| Project revision: Manage in-country consultations, prepare revision proposals | Accountable | Responsible | Consulted | Consulted | n/a |  | n/a | n/a | Informed |  |  | n/a | n/a | Consulted | Consulted | Consulted | n/a | n/a | n/a | n/a |  | Consulted | Consulted
| Project revision: quality assurance and submission to GEF for approval by GEF Secretariat/Council | n/a | Informed | Informed | Informed | Consulted |  | n/a | Consulted | Informed |  |  | n/a | n/a | Accountable | Responsible | Consulted | Consulted | Responsible | Consulted
| Project unfunded extension: Manage in-country consultations, prepare documentation | Accountable | Responsible | Consulted | Consulted | n/a |  | n/a | n/a | Informed |  |  | n/a | Consulted | n/a | Consulted | Consulted | n/a | n/a | n/a | Informed |  | Consulted | Responsible | n/a | n/a
| Project unfunded extension: quality assurance and approval and reporting to GEF | Informed | Informed | Informed | Informed | Consulted |  | n/a | n/a | Informed |  |  | Accountable | Informed | Responsible | Informed | Consulted | n/a | Responsible | n/a | n/a |  | n/a | n/a | n/a | n/a
| TE and GEF core indicators: Manage contracting and in-country consultation process according to GEF deadlines and guidance; draft management response; upload relevant documentation to UNDP ERC | Accountable | Responsible | Consulted | Consulted | Consulted |  | n/a | n/a | Informed |  |  | n/a | Informed | n/a | Consulted | Consulted | n/a | Consulted | Consulted
| TE and GEF core indicators: quality assurance, provide input to CO on management response, sign off on TE report, and submission to GEF Secretariat and IEO | Informed | n/a | Informed | Informed | Consulted |  | n/a | Consulted | Informed |  |  | n/a | Accountable | n/a | Consulted | Consulted | n/a | Responsible | Responsible | n/a |  | Consulted | Consulted | n/a | n/a
Project closure | Operational and financial closure: undertake as per PPM requirements | Accountable | Responsible | n/a | Consulted | Consulted |  | n/a | n/a | Informed |  |  | n/a | n/a | n/a | n/a | Consulted | Informed | Consulted | n/a | n/a |  | Informed | Consulted | n/a | n/a
| Operational and financial closure: verification and reporting to GEF Secretariat and GEF trustee | n/a | n/a | Consulted | Informed | Consulted |  | n/a | n/a | Informed |  |  | n/a | n/a | n/a | Responsible | Consulted | Accountable | Responsible | n/a | n/a |  | n/a | n/a | n/a | n/a